## Slide 1: EVENT MANAGEMENT

## Slide 2: Planning Overview
Events Planning Overview
Steps to take
Brainstorm and develop your event concept.
Create an Event Organising Committee
Health and Safety Considerations (8 Weeks out or earlier)
Financial plan/ secure Sponsorship (6 Weeks)
Venue
Equipment hire
Finalise Plans
Contingency
After the Event

## Slide 3: BRAINSTORM & DEVELOP YOUR EVENT CONCEPT
Step 1: Brainstorm and develop your event concept
When coming up with event ideas it’s crucial that you look at them from an outsider’s perspective. When developing events, it’s important you address these three key areas.
Marketing Potential – ‘Is it worth it?’
Operational Capabilities – ‘Can we do it?’
Financial Capabilities – ‘Can we pay for it?’

## Slide 4: BRAINSTORM & DEVELOP YOUR EVENT CONCEPT
Marketing Potential
When we say marketing potential we explicitly mean ‘will people attend.’ Due to the busy nature of a college campus, there is an enormous choice of events to go to. For this reason, it is important you ask yourself will enough people attend your event instead of similar events that week. If the answer is not a resounding yes, it is likely that the event will struggle to gain traction.
Operational Capabilities
This question revolves around the skills and permissions required to run your event. For example, if you are a new society with no previous experience of running events, it is unlikely you will be able to undertake the tricky path of organising a Ball. Outside of having the relevant skills and experiences to run an event, permissions and Health & Safety considerations can often be a critical oversight at this stage. Questioning how your event will be sanctioned will be crucial for its success in the long run.
Financial Capabilities
How you will finance your event is another key factor in whether it will be possible or not. Club and society events are usually of a fundraising nature. For this reason, your event should be seeking to make a profit to provide funds to reinvest in the clubs or socs’ activities. It is very important a cash flow estimate is completed as many clubs/societies struggle with funds approximately 3-4 weeks out as ticket sales have still to take off, yet deposits and invoices have to be paid.

## Slide 5: HEALTH & SAFETY
Health and Safety Considerations
The 3 key areas regarding Health and Safety and events are:
Permissions
Insurance
Risk Assessments/Event Management Plan
First Aid
Permissions
For large events approval must be obtained. Before deciding on any event call to the Clubs and Societies Office to discuss your plans and receive initial approval. When holding an event off campus – Insurance, Fire Safety signed and in place by the venue owners. Contracts must be approved by the C and S Office before signing. All commercial business are required to pay to come on campus.
Insurance
The relevant insurance needs to be sought as far in advance prior to an event due to the lengthy nature of the process. For that reason, when talking to the C & S Office enquire about the insurance cover needed for the safe running of your event. Anyone dealing with outside catering companies must be supply the relevant food and safety documentation.

## Slide 6: HEALTH & SAFETY
Risk Assessments
Risk is something that needs to be thoroughly assessed and reduced prior to an event. Risk Assessments forms are often necessary for events and should help assess where possible risks can be found. It is important that risk assessments are seen as a crucial and natural element to events and should not be a box ticking exercise or an afterthought.
First Aid
The organising committee is responsible for ensuring that there is adequate first aid provision for the duration of the event. It should be organised in consultation with Clubs and Socs Office. A specific location should be designated as a first aid station and this location must be known by all. If a qualified club/soc member is providing first aid cover, they should not participate in the event itself.

## Slide 7: FINANCES
Finance planning /obtaining sponsorship
Finance is the area where many events have struggled in the past, so it is very important that a comprehensive plan is in place beforehand. When completing an ‘Event and Finance Plan’ it is crucial that you tally your costs and expenses first and add a contingency, and then price your tickets accordingly. Under-pricing tickets is a key reason why events struggle financially. If you feel that the ticket price is too high, you must go back and cut down on your costs to lower prices. Cash flow shortages are issues regarding the payment of event costs prior to the event income being received (ticket sales, raffles etc.) Due to the relatively unknown nature of some incomes (how many people will turn up, will many raffle tickets will we sell etc.) it is important to try cover major costs prior to the event by means of sponsorship, pre-sold tickets and early bird tickets.

## Slide 8: VENUE
Decide on a venue
When deciding on a venue (especially off campus) it’s vital to shop around and seek advice and reviews. Making sure your venue is suitable location wise, financially and operationally is crucial and can be achieved by making visits, making floor plans, checklists and asking the venue any other questions you may have. If the venue is on campus, it is important you book well in advance to avoid date clashes and to seek the relative permissions. With regard to balls or other large venue bookings it is crucial to contact Clubs and Socs Office before any deposit is paid. All C & S organizing a ball should contact the office at the beginning of the academic year.

## Slide 9: EQUIPMENT HIRE
Equipment Hire
Equipment hire is quite an expensive element of an event . If you feel you don’t have the required tech skills to pull off the event there are vendors that offer to hire and set up the equipment for you, obviously with the added costs of such a service.
Possibility of workshops in this area for performance societies.

## Slide 10: FINALISING PLANS
Confirmation and finalisation of major event components.
About 3 weeks approx. out from your event you should be certain that all the major items are in place and ready to go. This final review point before selling tickets also allows for a possible cancellation or scaling back of the event with minimal losses before any major payments are made. If the proper insurance, permissions, equipment, venues and people are in place you can be hopeful that you haven’t made any critical oversights.

## Slide 11: FINALISING PLANS
Promotional plan and ticket sales
Once a price, venue, date and sponsors are finalised it’s time to decide how you will sell your tickets. Pre-selling tickets whether it’s through physical sales or online platforms is recommended to help gauge numbers prior to an event. A promotional plan through numerous channels should be devised and some unique content (promo videos, etc.) should be utilised to differentiate your event.
A content calendar is a very useful tool for PROs in the lead up to large scale events. This will remind you what is to be posted during the promotional blitz. Also allowing for a consistent and organised approach to your social media marketing.

## Slide 12: FINAL PLANS - SMALL STUFF
Don’t forget small stuff
In the run up to the event it’s time to begin prepping the often, forgotten elements of an event that can sometimes leads to embarrassing oversights. Now is the time to start worrying around your raffle tickets, decorations, blue tack, sellotape, extension leads, cleaning supplies, black bags, speeches and thank you gifts. It’s these minor details that can eliminate a lot of unnecessary stress on the day and make it a lot easier to deal with larger issues if they arise.

## Slide 13: CONTINGENCY
Contingency and emergency issues
It’s important that any last minute, changes or large scale, emergencies be dealt with immediately. If the problem can be rectified do so as soon as possible, however, if the issue is more serious it’s important your committee stands back and objectively analyses the information at hand. Your responsibility lies in ensuring that the event is also safe and sustainable. If the event is beginning to look risky beyond your control (inclement weather) or if the event is going to have a major negative effect on the society in the future, it is crucial to re-evaluate its viability. Again, during situations like this it is always helpful to contact the Clubs and Socs Office.

## Slide 14: AFTER THE EVENT
Post Event Review
Planning a good post event review is an important part of the event management process. Here are the main tasks in a post event review:
Complete paperwork.
Finalise lodgements & payments.
Write a review of event and capture what went well, and lessons learned.
Send any sponsors an event summary and thank you letter.
Thank all attendees on social media.
Post event pictures & videos as soon as possible.

## Slide 15: Event Checklist
Developed the concept and assessed the events viability.
Completed an ‘Event and Finance Plan’ or a ‘Ball Event and Finance Plan’
Met with the team in Clubs and Sos Office to discuss its viability.
Health and safety criteria met, risk assessments completed, and necessary insurance sought.
Sponsorship sought and detailed financial plan completed.
Venue decided upon.
Necessary equipment researched, priced and booked.
Confirm all major components are in place before the event is promoted..
Tickets are printed or online ready for sale.
Promotional plan in place and timetable for ticket sales.
Double check with all stakeholders expected on the night to confirm their attendance, set up times, sound checks (medics, security, speakers etc.),
Pre-event meeting with all organisers and volunteers completed.
Photographer/ videographer confirmed.
During the event remove, count and secure cash from ticket sales at the door regularly. Make sure two people are tasked with this job to provide accountability and certainty.
Assess and take note of any issues that arise on the night and report any damage to equipment.
Pay all outstanding invoices.